## Sheet1
Bug ID | Module | Bug Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status
BUG_001 | Login | Login button not working | Login button is not responding after clicking | 1. Open Login page 2. Enter valid credentials 3. Click Login | User should login successfully | Nothing happens after clicking Login | Critical | High | Open
BUG_002 | Login | Password accepts only spaces | Password field allows only spaces and login succeeds | 1. Open Login page 2. Enter spaces in password 3. Click Login | Validation error should show | Login accepted | High | High | Open
BUG_003 | Signup | Duplicate email allowed | Same email can be registered multiple times | 1. Register with existing email 2. Submit form | Error message should display | Account created again | High | High | Open
BUG_004 | Forgot Password | Reset email not sent | Reset password email not received | 1. Click Forgot Password 2. Enter valid email 3. Submit | Email should be sent | No email received | High | Medium | Open
BUG_005 | UI | Login page alignment issue | UI elements not aligned in mobile view | 1. Open site in mobile view | UI should be proper | Button overlaps text field | Low | Medium | Open
BUG_006 | Security | Password visible in inspect | Password visible in page source | 1. Inspect password field | Password should be hidden | Password is visible | Critical | High | Open
BUG_007 | Session | Back button login issue | After logout, back button logs user in again | 1. Login 2. Logout 3. Click Back button | User should remain logged out | User logs in again | High | High | Open